## Sheet1
| PROJECT START: | 2025-08-18 |  |  |  |  | 2025-08-18 | [6 empty] | 2025-08-22 | [6 empty] | 2025-08-29 | [6 empty] | 2025-09-07 | [6 empty] | 2025-09-14
[7 empty] | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31 | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-20 | 2025-09-21
| TASK | ASSIGNED TO | START | END | Duration | PROGRESS | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
1 | Phase 1: Project Planning & Estimation | All Members | 2025-08-18 | 2025-08-22 | 5 | 100% | bar: 2025-08-18
1.1 | Establish Project Scope & Analyze Feasibility | Morshed, Tanjim | 2025-08-18 | 2025-08-18 | 1 | 100% | bar: 2025-08-18
1.2 | Task Decomposition & WBS Creation | Jahidul, Nahin | 2025-08-19 | 2025-08-19 | 1 | 100% | bar: 2025-08-19
1.3 | Effort Estimation using LOC & COCOMO Models | All Members | 2025-08-20 | 2025-08-20 | 1 | 100% | bar: 2025-08-20
1.4 | Develop Project Schedule & Define Milestones | All Members | 2025-02-21 | 2025-02-21 | 1 | 100% | bar: 2025-08-21
1.5 | Perform Risk Analysis & Build Risk Table | Morshed, Nahin | 2025-08-22 | 2025-08-22 | 1 | 100% | bar: 2025-08-22
2 | Phase 2: Software | All Members | 2025-08-25 | 2025-08-29 | 5 | 100% | bar: 2025-08-23
2.1 | Architectural Design (High-Level Structure) | Jahidul, Tanjim | 2025-08-25 | 2025-08-26 | 2 | 100% | bar: 2025-08-26
2.2 | Component-Level Design (Modularity & Cohesion) | Morshed, Nahin | 2025-08-27 | 2025-08-27 | 1 | 100% | bar: 2025-08-27
2.3 | Database Design (ERD Modeling) | Jahidul, Tanjim | 2025-08-28 | 2025-08-28 | 1 | 100% | bar: 2025-08-28
2.4 | Interface Design (UI/UX Wireframing) | Morshed, Nahin | 2025-08-29 | 2025-08-29 | 1 | 100% | bar: 2025-08-29
3 | Phase 3: Construction & Implementation | All Members | 2025-09-01 | 2025-09-09 | 7 | 100% | bar: 2025-08-30
3.1 | Setup SCM Repository (Version Control) | Jahidul, Morshed | 2025-09-01 | 2025-09-01 | 1 | 100% | bar: 2025-09-01
3.2 | Backend: Code Generation & Unit Testing | Jahidul, Tanjim | 2025-09-02 | 2025-09-05 | 4 | 100% | bar: 2025-09-02 to 2025-09-05
3.3 | Frontend: Code Generation & Component Testing | Morshed, Nahin | 2025-09-04 | 2025-09-09 | 4 | 100% | bar: 2025-09-04 to 2025-09-09
4 | Phase 4: Integration & Validation Testing | All Members | 2025-09-10 | 2025-09-16 | 5 | 100% | bar: 2025-09-09
4.1 | System Integration (Connecting Modules) | All Members | 2025-09-10 | 2025-09-11 | 2 | 100% | bar: 2025-09-10 to 2025-09-11
4.2 | Conduct User Acceptance Testing (UAT) | Morshed, Nahin | 2025-09-12 | 2025-09-12 | 1 | 100% | bar: 2025-09-12
4.3 | Final Bug Fixing & Code Inspection | All Members | 2025-09-15 | 2025-09-15 | 1 | 100% | bar: 2025-09-15
4.4 | Perform Quality Assurance & Feature-level Testing | Jahidul, Tanjim | 2025-09-16 | 2025-09-16 | 1 | 100% | bar: 2025-09-16
5 | Phase 5: Deployment & Project Closure | All Members | 2025-09-17 | 2025-09-18 | 2 | 100% | bar: 2025-09-16
5.1 | Establish Production Baseline & Deploy Application | Jahidul, Tanjim | 2025-09-17 | 2025-09-17 | 1 | 100% | bar: 2025-09-17
5.2 | Prepare Final Report & User Manual | Morshed, Nahin | 2025-09-17 | 2025-09-18 | 2 | 100% | bar: 2025-09-17 to 2025-09-18
5.3 | Prepare Final Project Presentation | All Members | 2025-09-18 | 2025-09-18 | 1 | 100% | bar: 2025-09-18